## Sheet1
Great Grant Giveaway Communications & Next Steps Timeline
PHASE 1 (Message Creation - to be shared with staff and Trustees)
2023-10-04 | Timeline Presentation to Leadership Team
10/11 - 11/1 | Messaging meetings with key staff and determining 2024 Corporate Partner benefits
2023-10-30 | Message presentation to Leadership Team
2023-10-31 | Message presented to full staff at staff meeting
2023-11-17 | Memo/Presentation Prepped for Executive Committee
2023-11-28 | Presented to Executive Committee
2023-11-28 | Conversations with other Board Members
2023-11-28 | Email to Full Board + Advancement Committee
2023-11-29 | Board Packet Posting
Late November/Early December | Find a Faciliator for Community Conversations
2023-12-05 | Q4 Board Meeting
PHASE 2 (Message to be shared with Donors, Nonprofits, Corporate Partners, Attendees, General Public)
2023-12-13 | Next steps conversation with key staff
January/February 2024 | Release message to public, Prep with Faciliator, Promotion of Community Converstaions
March/April/May 2024 | GGG Community Conversations
June/July 2024 | Reimagining Great Grant Giveaway
August - December 2024 | Planning, preparing
2025-01-01 | Save the Date - New GGG 2025